## Slide 1
Six Sigma Project-Story-Book
for the project: Public Garbage Littering in …
Green-Belt Candidate:
your name
eMail-adress
Technische Universität München

## Slide 2: Note: Summarize the key message of this slide in the header (here) and footer (below) …
... in one or two easy-to-understand statements for Six Sigma non-experts
Six Sigma > Instruction >> Layout Template
Interpretation and implication
This is the place for your interpretation of the results. What is important to know?
Furthermore, the consequences and implications arising from the results, and your interpretation, and the next step should be described.
** place for references
Results
Important results and details:
Indication of specifics and/ or
Indication of abnormalities and/ or
Indication of priorities
Tool-Frame
This is the frame for tools, pictures, charts, graphs, tables, …
It is not necessary to use exactly the size of these frames -
other sizes and arrangements are of course permitted.
It is important that the key results can be derived from this picture.
Please use this template for all of your slides, as far as possible.
1.
2.
3.

## Slide 3
Six Sigma > Instruction >> Checklist
ü
Checklist for your documentation …
... and reference for your MBB in the DMAIC phase reviews

## Slide 4
Introduction
Six Sigma > Project-Story-Book

## Slide 5
Short introduction of the Green-Belt candidate, his/ her sponsor and the company
Green Belt:
Sponsor:
Company:
Picture of you
Picture of your sponsor
ü
Six Sigma > Personal Introduction
voluntary for Sustainability-Projects
voluntary for Sustainability-Projects
… if possible, with a picture of you and your sponsor

## Slide 6
Scan of the signed confirmation eMail of the project sponsor
Scan of the signed confirmation mail of the sponsor
Six Sigma > Personal Introduction
voluntary for Sustainability-Projects

## Slide 7
Scan of TUM Lean Six Sigma Yellow Belt Certificate
Six Sigma > Personal Introduction

## Slide 8
pre-DEFINE
Identification and Definition of a Six Sigma Project
Six Sigma

## Slide 9
Reviews
Data
Photos
Overview
Items typically littered:
Plastic bottles, some of them found in proximity to trash cans.
Big bags full of trash typically broken by animals trying to find food.
PPE Masks.
Paper: packaging and office supplies
Little pieces of litter: plastic remains, beverage packaging.
4 Reviews
Six Sigma > Define > Project Ilustration
ü
Problems: Gemba Walk with Examples of Littering
Example: please replace example content by information about your project

## Slide 10
About roadway and waterways…
The Study estimates nearly 50 billion pieces of litter along U.S. roadways and waterways at the time of the Study. For many, that is an unfathomable number. However, when accounting for the U.S. population, 50 billion pieces of litter equate to 152 pieces of litter for every U.S. resident. This is a large number but is something to which individuals can relate. People can visualize 152 pieces of litter where they live, and they can begin to see that the litter problem can be solved.
About the items littered…
Litter made from plastic comprises 38.6 percent of all litter across waterways and roadways combined.4 Nine out of ten pieces of litter on the ground in the U.S. were under four inches in size. Though smaller litter may be less visible, it remains the dominant type of litter in the United States.
Cigarette butts continue to be the single most littered item in the United States, even though cigarette butt litter has declined dramatically since 2009.
Plastic films, both general use films and food-packaging films, such as candy wrappers or snack bags, represent the second and third most littered items in America.
Nearly 350 million plastic bags were littered on United States roadways and waterways. The vast majority (94.6 percent) of plastic bags littered were not trash bags, but other types of bags (i.e., retail store plastic bags).
About the people…
Across the nation, U.S. residents agree that litter is a problem where they live. Ninety percent (90%) of U.S. residents reported that litter is a problem in their state.
Americans understand that litter has a strong negative impact on their communities. Large majorities of U.S. residents (75 to 97 percent) recognize that litter negatively affects the environment, waterways, property taxes, home values, tourism and businesses, quality of life, and health and safety in their communities.
Source: Keep America Beautiful
2020 NATIONAL LITTER STUDY
Summary Report: May 2021
https://kab.org/litter-study/
The study comprises four major components: a survey examining public attitudes about litter, a visible litter survey that provides an estimate of the litter on the ground across the USA, behavioral observations that shed light on littering behavior in public and a survey that estimates the public costs of litter in the United States.
Copyright© Keep America Beautiful, Inc.
Overview
Reviews
Data
Photos
4 Reviews
Effect: Customer (Dis-)Satisfaction
Six Sigma > Define > Project Ilustration
ü
Example: please replace example content by information about your project

## Slide 11
Effect: Littering Costs
Six Sigma > Operating Budget for Citiy Beautifcation in Toronto (Dr. Iman Soltani, Canada)
2019 Staff Recommended Operating Budget: $36.8M
Litter Pick-up, Park and
Street Bin Collection-
Residual Waste - 1 to 7
times per week
Key Service Levels
Litter Pick-up, Park and
Street Bin Collection-
Single Stream Recycling - 1 to 7
times per week
Special Events
Collection - Waste,
Recycling, Organics -
On Demand
City of Toronto Population (2019): 2,731,571
Operating Budget per capita ~ $13.5
https://www.toronto.ca/legdocs/mmis/2019/bu/bgrd/backgroundfile-123937.pdf
City Beautification service provides collection services within the public realm to all residents and visitors city-wide to support a clean city.
Activities include litter pick-up, Special Events clean-up, Parks Bin and Street Litter Bin management.
Staff Recommended Operating Budget: $36.8M, which equals about $13.5 per capita (2019).
Litter pick-up (48%), Parks Bins (32%), and Street Litter Bins (17%) are respectively, required the highest budgets.
$0.313M New/enhanced funding is assigned to initiate additional litter pickup – Alleys, Laneways and Parks (Subdomain of City Beautification)
ü
Example: please replace example content by information about your project

## Slide 12
Effects (Z), Problems (Y), Causes (x) and Solutions (S) hierarchically structured in a fault-tree
This Problem Model will be further specified and statistically analysed to identify Root Causes as Interfaces for Solutions
Customer dissatisfied (S)
Customer compensation claims (C)
Company revenue losses
Company quality costs increased (C)
Effects (Z)
Cookie ingredients > 50 g waste (C)
Cookie delivery 1 w. early (A)
Cookie diameter > 10 cm
(Q)
Cookie energy waste (C)
Cookie taste bad (Q)
Problems (Y)
Chocolate nibbled from ingredients (A)
Order specification on taste ambiguous (I)
Date on calendar wrong (R)
Timer setup wrong (R)
Oven extremely preheated (R)
Cookies shaped variably (M)
Ingredients individually determined (M)
Triggering
Causes (x)
.
.
.
.
Root Causes (x)
Solutions (S)
time
Use cookie blanks (c)
Determine correct oven temperature (a)
Forbid nibbling (e)
Six Sigma > Method >> Model Observations
Example: please replace example content by information about your project

## Slide 13
DMAIC > Project-Definition
Example: please replace example content by information about your project
Results
Interpretation and implication
Note: Summarize the key message of this slide in the header (here) and footer (below) …
... in one or two easy-to-understand statements for Six Sigma non-experts

## Slide 14
DEFINE
SIPOC, Voice to Criticals, Project-Charter, Stakeholder Communication
Six Sigma

## Slide 15
DMAIC > SIPOC
Note: Summarize the key message of this slide in the header (here) and footer (below) …
... in one or two easy-to-understand statements for Six Sigma non-experts
Interpretation and implication
Results
Example: please replace example content by information about your project

## Slide 16: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > Voice to Criticals >> Summary and details
... in one or two easy-to-understand statements for Six Sigma non-experts
Interpretation and implication
Results
Example: please replace example content by information about your project

## Slide 17: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > Voice to Criticals >> Charts
... in one or two easy-to-understand statements for Six Sigma non-experts
Interpretation and implication
Results
Example: please replace example content by information about your project

## Slide 18: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > Project-Charter
... in one or two easy-to-understand statements for Six Sigma non-experts
Interpretation and implication
Results
Example: please replace example content by information about your project

## Slide 19: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > Stakeholder Communication
... in one or two easy-to-understand statements for Six Sigma non-experts
Interpretation and implication
Results
Example: please replace example content by information about your project

## Slide 20: Results of the DEFINE-Steering
DMAIC > Steering-Results
Only proceed to the next phase after a positive decision of MBB and Sponsor
Define-Steering |  |  |  | 
Tool | Application | Documentation | Comment | Decision
Introduction, Presentation of Critical Product/ Service | ok | ok | see checklist ref #: | Master-Black-Belt
Project-Topic | ok | ok | see checklist ref #: | Dr. Reiner Hutwelker reiner.hutwelker@tum.de
Project-Definition | ok | ok | see checklist ref #: | 1-Jan-2022
SIPOC | ok | ok | see checklist ref #: | passed/ failed
VoC/ VoB/ CtQ (Voice to Criticals) | ok | ok | see checklist ref #: | Sponsor
Project-Charter | ok | ok | see checklist ref #: | name/ email
Stakeholder Communication | ok | ok | see checklist ref #: | 1-Jan-2022
Additonal Notes |  |  | =$E$4 | passed/ failed

## Slide 21
MEASURE
Six Sigma
Input-Analysis, Process-Mapping/ -Analysis, C&E-Matrix, Data-Collection-Plan, Hypothesis

## Slide 22: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > Input-Analysis
... in one or two easy-to-understand statements for Six Sigma non-experts
Interpretation and implication
Results
Example: please replace example content by information about your project
Notes: Editing note: in Excel fie

## Slide 23: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > Process-Mapping-Analysis
... in one or two easy-to-understand statements for Six Sigma non-experts
Example: please replace example content by information about your project

## Slide 24: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > Process-Mapping-Analysis
... in one or two easy-to-understand statements for Six Sigma non-experts
Interpretation and implication
Results
Example: please replace example content
by information about your project

## Slide 25: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > Process-Mapping-Analysis >> Documentation of 1st workshop
... in one or two easy-to-understand statements for Six Sigma non-experts
Picture(s) of workshop participants in front of workshop results
Tool-Frame
(Picture of the original workshop flipchart with the Process-Mapping/ -Analysis)
optional

## Slide 26: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > C&E Matrix
... in one or two easy-to-understand statements for Six Sigma non-experts
Interpretation and implication
Results
Example: please replace example content by information about your project

## Slide 27: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > C&E Matrix >> C&E Heatmap
... in one or two easy-to-understand statements for Six Sigma non-experts
Interpretation and implication
Results
Example: please replace example content
by information about your project

## Slide 28: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > Data Collection Plan
... in one or two easy-to-understand statements for Six Sigma non-experts
Example: please replace example content by information about your project
Notes: Editing note: check the word "measurands" again

## Slide 29: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > Hypotheses
3.
2.
1.
... in one or two easy-to-understand statements for Six Sigma non-experts
Interpretation and implication
Results
Example: please replace example content by information about your project

## Slide 30: Note: Summarize the key message of this slide in the header (here) and footer (below) …
2.
1.
... in one or two easy-to-understand statements for Six Sigma non-experts
Interpretation and implication
Results
Example: please replace example content by information about your project
These templates should be used to facilitate understanding and to formulate additional hypotheses:
Difference-Hypotheses |  |  |  |  | 
There is a difference in: (Y) | between: Levels of (x) | Scale Level of Y | Scale Level of x | Graphical Representation: | Statistical Test:
The taste rating of Cookies | Types of Cookies (Vanilla vs. Chocolate) | cardinal | nominal | Box-Plot | t-Test/ ANOVA
… | … | … | … | … | …
Relationship-Hypotheses |  |  |  |  | 
There is a relationship between: x … | … and Y | Scale Level of Y | Scale Level of x | Graphical Representation: | Statistical Test:
Amount of Chocolate in ingredients | Rating of Taste | cardinal | cardinal | Scatter Plot | Correlation/ Regression
… | … | … | … | … | …
sigmaGuide contains this template: - Hypotheses (Templates)
DMAIC > Hypotheses

## Slide 31: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > Mintab Worksheet
... in one or two easy-to-understand statements for Six Sigma non-experts
Interpretation and implication
Results
Example: please replace example content by information about your project
Please make sure to include all variables - with at least some dummy data - that you want to collect and analyse.

## Slide 32: Results of the MEASURE-Steering
DMAIC > Steering-Results
Only proceed to the next phase after a positive decision of MBB and Sponsor
Measure-Steering |  |  |  | 
Tool | Application | Documentation | Comment | Decision
Input-Analysis | ok | ok | see checklist ref #: | Master-Black-Belt
Process-Mapping/ -Analysis | ok | ok | see checklist ref #: | Dr. Reiner Hutwelker reiner.hutwelker@tum.de
C&E-Matrix & -Heatmap / Summary for Sponsor | ok | ok | see checklist ref #: | 1-Jan-2022
Data-Collection-Plan | ok | ok | see checklist ref #: | passed/ failed
MSA (optional) | ok | ok | see checklist ref #: | Sponsor
Hypotheses | ok | ok | see checklist ref #: | name/ email
Data-Worksheet | ok | ok | see checklist ref #: | 1-Jan-2022
Additonal Notes |  |  | =$E$4 | passed/ failed

## Slide 33
Analyse
Six Sigma
Data Evaluation, Process Performance, Test of Hypotheses, Root Cause Analysis

## Slide 34: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > Graphical Evaluation of collected data
... in one or two easy-to-understand statements for Six Sigma non-experts
Interpretation and implication
Results
Example: please replace example content by information about your project

## Slide 35
DMAIC > Process Performance >> Control Chart
Interpretation and implication
Results
Note: Summarize the key message of this slide in the header (here) and footer (below) …
... in one or two easy-to-understand statements for Six Sigma non-experts
Example: please replace example content
by information about your project

## Slide 36: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > Process Performance >> Process Capability
... in one or two easy-to-understand statements for Six Sigma non-experts
Interpretation and implication
Results
Example: please replace example content
by information about your project
Notes: Check "Pp/ Ppk Capability Index "
Can you use "quantitatively" scaled instead of "cardinal"? or use both terms?

## Slide 37: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > Test of Hypothesis
1.
... in one or two easy-to-understand statements for Six Sigma non-experts
Interpretation and implication
Results
Example: please replace example content by information about your project
Notes: Check "Pp/ Ppk Capability Index "
Can you use "quantitatively" scaled instead of "cardinal"? or use both terms?

## Slide 38: Note: Summarize the key message of this slide in the header (here) and footer (below) …
2.
DMAIC > Test of Hypothesis
... in one or two easy-to-understand statements for Six Sigma non-experts
Example: please replace example content by information about your project
Interpretation and implication
Results
Notes: Check "Pp/ Ppk Capability Index "
Can you use "quantitatively" scaled instead of "cardinal"? or use both terms?

## Slide 39
3.
DMAIC > Test of Hypothesis
Note: Summarize the key message of this slide in the header (here) and footer (below) …
... in one or two easy-to-understand statements for Six Sigma non-experts
Example: please replace example content by information about your project
Interpretation and implication
Results
Notes: Check "Pp/ Ppk Capability Index "
Can you use "quantitatively" scaled instead of "cardinal"? or use both terms?

## Slide 40: DMAIC > Root Cause Analysis
Root Cause Analysis by Hierarchy Tree
Analysis strategy: Combine quantitative statistical results and logical arguments …
… to identify root causes by (statistically confirmed) assumptions about causal relationships
Cookie Taste bad
(Y1)
Problem
Problem-Focus
(Prioritization by: Pareto Diagram, 2-Sample-Proportion, t-Test, ANOVA or separate hierarchy tree)
Chocolate-Cookie
Taste bad
(Y1a)
Vanilla-Cookie Taste bad
(Y1b)
Cause-Level
(Causation by trigger)
Amount of chocolate too low (x1)
Chef has too few opportunities to nibble on chocolate (x1.2.3)
Chef has grown and now reaches the ingredients on the table (x1.2.2)
Chef ignores the kitchen standards (x1.2.1)
3. Cause-Level (intermediate causation)
4. Cause-Level (intermediate causation)
Information in recipe exceeds the Chef's capabilities (x1.2.1.1)
The logical links between causes determine the scope of necessary solutions:
or: select both
and: select (at least) one
Manager has restricted the consumption of chocolate (x1.2.3.1)
Too much chocolate is unhealthy for young Chefs (x1.2.3.1.1)
Difference Hypothesis
Y1 =/ ≠ Y2 …
(Test: Chi2, t-Test/ ANOVA)
D= 1,52 grades
1.
D= 3,1 grades in Taste
between conditions
3.
Relationship Hypothesis
Y= f(x)
(Test: Correlation/ Regression)
R2= 96,5%
2.
D= 5,5 grades in Amount
between conditions
4.
Develop solutions to
Eliminate,
Adjust or
Circumvent (root) causes
n. Cause-Level (Causation by root cause)
Manager overestimated the cognitive capabilities of the Chef (x1.2.1.1.1)
Finger pointing
Body growth is part of the development of young Chefs (x1.2.2.1)
Unchangeable
fact of reality
Scale incorrectly calibrated (x1.3)
Reality check
2. Cause-Level (intermediate causation)
Chef did NOT nibble on Chocolate of ingredients (x1.1)
Chef nibbles on Chocolate of ingredients (x1.2)
Reality check
Expiry date of ingredients exceeded (x1.4)
or
and
Interpretation and implication
Results
Example: please replace example content by information about your project

## Slide 41: Note: Summarize the key message of this slide in the header (here) and footer (below) …
... in one or two easy-to-understand statements for Six Sigma non-experts
Picture(s) of workshop participants in front of workshop results
Tool-Frame
(Picture of the original workshop flipchart with the Root-Cause Analysis)
DMAIC > Root Cause Analysis >> Documentation of 2nd workshop
optional

## Slide 42: DMAIC > Summary
Interpretation and implication
Results
Note: Summarize the key message of this slide in the header (here) and footer (below) …
... in one or two easy-to-understand statements for Six Sigma non-experts
Example: please replace example content by information about your project

## Slide 43: Results of the ANALYSE-Steering
DMAIC > Steering-Results
Only proceed to the next phase after a positive decision of MBB and Sponsor
Analyse-Steering |  |  |  | 
Tool | Application | Documentation | Comment | Decision
Graphical Analysis | ok | ok | see checklist ref #: | Master-Black-Belt
Process-Capability | ok | ok | see checklist ref #: | Dr. Reiner Hutwelker reiner.hutwelker@tum.de
Control-Charts | ok | ok | see checklist ref #: | 1-Jan-2022
Statistical Tests of Hypotheses | ok | ok | see checklist ref #: | passed/ failed
Root-Cause-Analysis | ok | ok | see checklist ref #: | Sponsor
 |  |  |  | name/ email
 |  |  |  | 1-Jan-2022
Additonal Notes |  |  | =$E$4 | passed/ failed

## Slide 44
IMPROVE
Six Sigma
Development and selection of Solutions, Measures and risk prevention, Implementation

## Slide 45: Note: Summarize the key message of this slide in the header (here) and footer (below) …
Unfortunately, Excel sometimes does not display the names of the bubbles, so please supplement them manually.
DMAIC > Solution-Ideas
Interpretation and implication
Results
... in one or two easy-to-understand statements for Six Sigma non-experts
Example: please replace example content by information about your project

## Slide 46: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > Action-Plan
Interpretation and implication
Results
... in one or two easy-to-understand statements for Six Sigma non-experts
Example: please replace example content by information about your project

## Slide 47: Note: Summarize the key message of this slide in the header (here) and footer (below) …
DMAIC > FMEA
Interpretation and implication
Results
... in one or two easy-to-understand statements for Six Sigma non-experts
Example: please replace example content by information about your project

## Slide 48: DMAIC > Summary
Interpretation and implication
Results
Note: Summarize the key message of this slide in the header (here) and footer (below) …
... in one or two easy-to-understand statements for Six Sigma non-experts
Example: please replace example content by information about your project

## Slide 49
Comprehensive presentation of the improvement of the critical product/ service …
… if possible, illustrated by pictures
Six Sigma > Project-Story-Book

## Slide 50: Results of the IMPROVE-Steering
DMAIC > Steering-Results
Only proceed to the next phase after a positive decision of MBB and Sponsor
Improve-Steering |  |  |  | 
Tool | Application | Documentation | Comment | Decision
Solution-Ideas | ok | ok | see checklist ref #: | Master-Black-Belt
DoE (optional) | ok | ok | see checklist ref #: | Dr. Reiner Hutwelker reiner.hutwelker@tum.de
Action-List | ok | ok | see checklist ref #: | 1-Jan-2022
FMEA | ok | ok | see checklist ref #: | passed/ failed
 |  |  |  | Sponsor
 |  |  |  | name/ email
 |  |  |  | 1-Jan-2022
Additonal Notes |  |  | =$E$4 | passed/ failed

## Slide 51
CONTROL
Six Sigma
Data-Evaluation, Process-Performance, Improvements & Benefits, Process-Management-Plan & Finalisation

## Slide 52
Results
DMAIC > Evaluation of new collected data
Interpretation and Implication
2.
a.
b.
Before/ After comparison of Cookie Taste rating
Before / After comparison Cookie defect frequencies
1a.
1b.
Example: please replace example content
by information about your project
Note: Summarize the key message of this slide in the header (here) and footer (below) …
... in one or two easy-to-understand statements for Six Sigma non-experts

## Slide 53
DMAIC > Process Performance >> Control Chart
Interpretation and implication
Results
Note: Summarize the key message of this slide in the header (here) and footer (below) …
... in one or two easy-to-understand statements for Six Sigma non-experts
Example: please replace example content
by information about your project

## Slide 54
DMAIC > Process Performance >> Process Capability
Interpretation and implication
Results
Note: Summarize the key message of this slide in the header (here) and footer (below) …
... in one or two easy-to-understand statements for Six Sigma non-experts
Example: please replace example content
by information about your project
Adapt Header and Footer
Notes: Check "Pp/ Ppk Capability Index "
Can you use "quantitatively" scaled instead of "cardinal"? or use both terms?

## Slide 55: Note: Summarize the key message of this slide in the header (here) and footer (below) …
Interpretation and implication
Results
... in one or two easy-to-understand statements for Six Sigma non-experts
Example: please replace example content
by information about your project
DMAIC > Improvements and Benefits >> Test of Hypothesis

## Slide 56: Note: Summarize the key message of this slide in the header (here) and footer (below) …
Interpretation and implication
Results
... in one or two easy-to-understand statements for Six Sigma non-experts
Example: please replace example content
by information about your project
DMAIC > Improvements and Benefits >> Test of Hypothesis

## Slide 57: DMAIC > Process-Management-Plan
Interpretation and implication
Results
Note: Summarize the key message of this slide in the header (here) and footer (below) …
... in one or two easy-to-understand statements for Six Sigma non-experts
Example: please replace example content by information about your project

## Slide 58: DMAIC > Process-Management-Plan >> Reaction-Plan
Interpretation and implication
Results
Note: Summarize the key message of this slide in the header (here) and footer (below) …
... in one or two easy-to-understand statements for Six Sigma non-experts
Detail of or complete reaction plan for the treatment of deviations in the process
optional

## Slide 59
Example: please replace example content by information about your project
Interpretation and Implication
Note: Summarize the key message of this slide in the header (here) and footer (below) …
... in one or two easy-to-understand statements for Six Sigma non-experts
DMAIC > Improvements and Benefits >> Financial and Other Benefits

## Slide 60: DMAIC > Review and Outlook
Interpretation and implication
Example: please replace example content by information about your project
Lessons learned
Potentials for further improvements

## Slide 61: Results of the CONTROL-Steering
DMAIC > Steering-Results
Only proceed to the next phase after a positive decision of MBB and Sponsor
Control-Steering |  |  |  | 
Tool | Application | Documentation | Comment | Decision
Graphical Analysis | ok | ok | see checklist ref #: | Master-Black-Belt
Process-Capability | ok | ok | see checklist ref #: | Dr. Reiner Hutwelker reiner.hutwelker@tum.de
Control-Charts | ok | ok | see checklist ref #: | 1-Jan-2022
Statistical Test of Improvement | ok | ok | see checklist ref #: | passed/ failed
Project-Management-Plan | ok | ok | see checklist ref #: | Sponsor
Summary & Benefits | ok | ok | see checklist ref #: | name/ email
Lessons Learned | ok | ok | see checklist ref #: | 1-Jan-2022
Additonal Notes |  |  | =$E$4 | passed/ failed

## Slide 62
End of this Project-Story-Book
Six Sigma process improvement methods and tools
Six Sigma
ü